## Team Tasks
Name | Phone | Assigned Task | Priority | Deadline | Status | Notes
عبدالله رفعت علام | 01091157494 | Team Leader + System Integration | Medium | 2026-02-22 | Not Started
اماني بلال ابو زيد | 01208185428 | ESP32 setup and initial testing | Medium | 2026-02-22 | Not Started
الاء محمد الحفني | 01143116077 | Ultrasonic sensor driver code | Medium | 2026-02-22 | Not Started
شمس محمد الديب | 01021639139 | Ultrasonic distance measurement | Medium | 2026-02-22 | Not Started
جومانة اسلام سليم | 01094562515 | Ultrasonic data filtering | Medium | 2026-02-22 | Not Started
عبدالرحمن سمير عامر | 01019847474 | Forward and backward motor control | Medium | 2026-02-22 | Not Started
عبدالرحمن محمد النجار | 01068016368 | Left and right turning control | Medium | 2026-02-22 | Not Started
شاهير محمد محمد | 01270400730 | LiDAR A1 setup with ESP32//LiDAR raw data reading | Medium | 2026-02-22 | Not Started
عزت عبد الرافع احمد | 01221300566 | Emergency stop system //Rotate-in-place movement control | Medium | 2026-02-22 | Not Started
شهد عبد الشافي الجيار | 01003831872 | Convert LiDAR data to distance points | Medium | 2026-02-22 | Not Started
ابراهيم فرج عبد الحليم | 01228081024 | Obstacle detection using LiDAR | Medium | 2026-02-22 | Not Started
شيماء عماد محمد | 01220124866 |  | Medium | 2026-02-22 | Not Started
فارس ابراهيم محمد | 01227820330 | Motor driver L298N driver code | Medium | 2026-02-22 | Not Started
نور ياسر عزام | 01277251600 | Motor speed control using PWM | Medium | 2026-02-22 | Not Started
معتز محمد عبدالرحمن | 01270071492 | ESP32-Arduino serial communication | Medium | 2026-02-22 | Not Started
محمد حماده شعبان | 01025844001 | Arduino command execution | Medium | 2026-02-22 | Not Started
عبدالله طارق محمد | 01277649198 | Movement state machine logic | Medium | 2026-02-22 | Not Started
شريف محمد عبده | 01227341321 | Sensor fusion (LiDAR + Ultrasonic) | Medium | 2026-02-22 | Not Started
كريم وائل محمد | 01124043918 |  | Medium | 2026-02-22 | Not Started
عاصم عبدالهادي نصر | 01289103997 | System testing and documentation | Medium | 2026-02-22 | Not Started
عمر عصام عبدالوهاب | 01095781636 |  | Medium | 2026-02-22 | Not Started
طارق احمد جميل | 01223020526 |  | Medium | 2026-02-22 | Not Started
يوسف ياقوت | 01279492911 |  | Medium | 2026-02-22 | Not Started
احمد فتحي احمد عبدالقادر | 01025601425 |  | Medium | 2026-02-22 | Not Started
فارس محمد محمود ابو ضيف | 01227671857 |  | Medium | 2026-02-22 | Not Started
محمد ابراهيم عبدالله الشربيني | 01550743448 |  | Medium | 2026-02-22 | Not Started